## Intro
Internal roadmap template
This is the top-line plan outlining the stages required to get your launch live. Each of the tactics listed in the second column will have multiple sub-tasks associated with them (head to our launch checklist for help with these) and may vary from launch-to-launch. This document is for internal use only and is often shared with other, relevant departments (like Product, Sales, Engineering, Operations, Customer Success, etc.) so they're up-to-speed with your timelines and what's required from them - and when.

## Template
Internal roadmap
[Company logo]
Remember, the below is not prescriptive and the overarching releases and tasks will need to be tailored to your business and launch tier.
|  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
|  | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC
Market analysis | bar: JAN
Pricing | bar: JAN to Q1 FEB
Persona research | bar: JAN to Q1 FEB
Positioning | bar: Q1 MAR
Goal setting | bar: Q1 MAR
Metrics dashboard | bar: Q1 MAR
New product | GTM plan | bar: Q1 MAR
Collateral creation | bar: Q1 MAR to Q1 APR
Sales enablement | bar: Q1 APR
Internal launch | bar: Q1 APR
External launch | bar: Q1 APR
New user onboarding | bar: Q1 APR to Q2 JUN
Analysis | bar: Q2 JUN
Feedback | bar: Q2 JUN
Collateral iterations
Enablement iterations
Goal setting | bar: Q2 MAY
Metrics dashboard | bar: Q2 MAY
GTM plan | bar: Q2 MAY
Asset management | bar: Q2 MAY
New feature | Sales enablement | bar: Q2 JUN
External launch | bar: Q2 JUN
New user onboarding | bar: Q2 JUN to Q3 AUG
Feedback | bar: Q3 AUG
Analysis | bar: Q3 AUG
Market analysis | bar: Q3 AUG
Pricing | bar: Q3 AUG
Persona research | bar: Q3 AUG
Positioning | bar: Q3 SEPT
Goal setting | bar: Q3 OCT
Metrics dashboard | bar: Q3 OCT
GTM plan | bar: Q3 OCT
New market | Collateral creation | bar: Q3 OCT
Sales enablement | bar: Q4 NOV
External launch | bar: Q4 DEC
New user onboarding | bar: Q4 DEC
Analysis | bar: Q4 DEC
Feedback | bar: Q4 DEC
Collateral iterations | bar: Q4 DEC
Enablement iterations | bar: Q4 DEC
Complete
In progress
Scheduled
Overdue