## Sales Enablement - checklist by
Stage | Deliverable/Activity | Tier 1 | Tier 2 | Tier 3 | Tier 4
Pre-Creative | Select a Launch Tier | x | x | x | x
Pre-Creative | Host kick-off meeting with stakeholders | x | x
Pre-Creative | Complete Sales Enablement Brief | x | x
Pre-Creative | Connect with sales ops—any changes to systems? | x
Pre-Creative | Connect with legal—any update to T&Cs? | x
Pre-Creative | Connect with PR/AR—media or analyst briefings | x
Pre-Creative | Connect with branded content and digital—associations, offers, webinar, or paid? | x | x
Pre-Creative | Connect with Support—any changes to documentation? | x | x
Pre-Creative | Submit creative request in Workfront using brief content | x | x | x | x
Creative | Host kickoff meeting with creative team and stakeholders | x | x | x
Creative | Manage + monitor asset creation | x | x | x | x
Creative | Complete draft of launch plan (plan overview + details, activities, owners, due dates) | x | x | x
2 weeks pre | Schedule Sales and Sales leader trainings | x | x
2 weeks pre | Review/approve launch plan with stakeholders | x | x | x
1 week pre | Host sales leader training | x | x
1 week pre | Draft internal comms (email, newsletter, sales leader talking points) | x | x | x
1 week pre | Draft descriptions and instructions to include in sales tools | x | x | x | x
1 week pre | Review/approve all internal and external assets and comms | x | x
1 week pre | Create Sales training outline | x | x
1 week pre | Set up Bit.ly links for internal communications | x | x
Launch | Time launch to Announcement | x | x | x
Launch | Schedule assets to post in LMS and/or enablement tool | x | x | x
Launch | Host session in all-hands or Town Hall event | x
Launch | Host sales trainings | x | x
Launch | Publish training assets (slides, videos, etc to enablement tool)
Launch | Publish internal comms (email, newsletter, slack) | x | x
1 month post | Communicate results back to leadership and stakeholder team(s) | x | x

## Tiers
Tier 1 | • New content or tactics • Very high impact • E.g. New ROI report, New sales process
Tier 2 | • Major update to existing content or tactics • High Impact • E.g. New sales deck, New sales play
Tier 3 | • Update to existing content, adding new copy or re-designed; slight shift in existing tactics • Medium Impact • E.g. Updated product one sheet, Updates to sales plays
Tier 4 | • Minor update to existing content, updating existing copy or design • Low Impact • E.g. Internal documentation, pricing updates on pricing one sheet