## How to use
Constructor Cost-Control Register
One spreadsheet that tells you what your home will cost in the end, and when the money has to be there.
What it is
| The question it answers | What will this home cost me in the end? The register adds up your contract price, approved variations, prime cost (PC) item and provisional sum (PS) adjustments, owner-supplied items and extras outside the contract, and compares that forecast final cost with your total budget. The difference is the contingency you have left.
| Colour key | Light yellow cells are for you to type in. Unshaded cells are calculated: leave them alone. A few yellow cells hold a starting formula (for example, quantity × rate); type over them with your own figure if you need to.
| Amounts | Keep every amount GST-inclusive, as your contract price is. Negative amounts are credits (for example, a PS that comes in under its allowance).
The sheets
| Cost plan (3.3, 3.5) | Your elemental estimate. One row per element of the house, then one row for each PC item and PS in your contract. Enter your own estimate and the builder's price for each; the difference shows where the gaps are. Set the group for each row (in the contract, owner-supplied, or outside the contract). Set your contingency percentage (the book suggests at least 10% of the contract price, more where the risk is higher). The total is your starting budget.
| Register (3.6) | One row per element, PC item and PS, filled from the Cost plan and the Log. It shows budget, contract amount, approved variations, PC/PS adjustments, what is spent or committed, what is quoted but not yet agreed, and your forecast final cost and over/under budget for each line. Use the yellow "Still to come" column for anything you expect but have not logged yet. The summary at the bottom is the same table as the book's example register.
| Log (3.6–3.7) | Every priced change, one row each: reference (V01, PS-01, PC-01…), date, register line, type, description, amount (+/−), status and evidence. Quoted counts as pending in the forecast; Agreed, Signed, Invoiced and Paid count as committed; Rejected is ignored. Use the types Owner-supplied and Extra outside contract for things you buy or contract yourself.
| Allowances (3.7) | Tracks each PC item and PS until it is closed: allowance, your selection or actual cost, the builder's margin on any overrun, and the adjustment (credits for under-runs carry no margin). Copy each adjustment into the Log; the check column tells you if the Log does not match.
| Progress claims (3.9) | The six stages of your payment schedule with the contract percentages (editable; the example schedule from Chapter 21.5 is filled in). Record each claim, whether you checked it, and what you paid. The sheet does the one-line reconciliation and warns you in red if claims or payments run ahead of the stage actually reached.
| Cash flow (3.8) | Month by month: each contract claim, other payments due, interest and rent, and how much comes from the loan and how much from your cash. Your money goes first: enter the loan amount and the sheet spends your share of the contract price before drawing on the loan. Variations, adjustments and extras are treated as cash. It warns you if your cash drops below the buffer you set.
The order to fill it in
| Step 1 | Before you sign: fill in the Cost plan from the builder's estimate (ask for it by element or trade) and your own quotes for the items outside the contract. List every PC item and PS with your own estimate beside each.
| Step 2 | Set your contingency percentage on the Cost plan. Check the starting budget against what you can afford.
| Step 3 | Enter the loan amount, your cash and a buffer on the Cash flow sheet, and the dates you expect each stage.
| Step 4 | Every time you agree to anything with a price, add it to the Log and check the forecast final cost on the Register before you sign.
| Step 5 | Close each PC item at selection on the Allowances sheet and copy the adjustment into the Log.
| Step 6 | Before every progress payment, fill in the claim on the Progress claims sheet, read the reconciliation and the warning, and update the Log and the Cash flow.
| Step 7 | At practical completion, do the full reconciliation and agree it in writing before you pay. After handover, record your actual final cost and keep the register with your home records.
Warning signs of cost drift (3.10)
| • | Forecast final cost rising every month, even by small amounts.
| • | Contingency spent faster than the build progresses. Half the contingency gone at base stage is a red flag.
| • | Many small variations, upgrades creeping in at selections, or variations for things the builder should have foreseen.
| • | PS items with no evidence, or adjustments arriving as round numbers.
| • | "We'll sort the paperwork later": unpriced verbal changes, or quotes for your own extras that keep growing.
| • | Delays: every extra week costs rent and interest, even if the contract price has not changed.
| • | If a first home grant value cap applies to you, variations can count towards it. Check your total before every variation.
General information only, not financial advice. Check every figure against your own contract, quotes and loan documents, and get advice where you need it.
From Chapter 3 of The Home Owner's Guide to Building Without Regret · constructor.net.au/book-resources

## Cost plan
Cost plan: your elemental estimate
Chapter 3.3. One figure per element, good enough to spot a gap. Mark every PC item and PS with the allowance and your own estimate.
# | Element / item | What it includes | Who prices it | Risk | Group | Quantity / basis | Rate | Your estimate | Builder's price | Difference (builder − yours) | Budget used in register | Notes
Elements of the house (3.3)
E01 | Preliminaries | Site establishment, temporary fencing, toilet, power, skip bins, scaffolding, supervision, insurance, home warranty premium | Builder (usually inside the contract price) | Low on a fixed-price contract | In contract
E02 | Approvals and consultants | Certifier, engineer, energy assessment, soil test, survey, council and plumbing fees | Builder or you (check the PSA) | Low to medium | In contract
E03 | Site works | Clearing, cut and fill, rock, retaining, piers, site drainage | Builder, often as a PS | High. The ground is the biggest unknown | In contract
E04 | Substructure | Slab or footings, termite management, under-slab plumbing | Builder | Medium. Depends on site class and engineering | In contract
E05 | Frame and roof | Wall and roof frames, trusses, bracing, tie-downs, roof cover, gutters | Builder | Low to medium | In contract
E06 | External envelope | Cladding or brickwork, windows, external doors, sarking, wall wrap, insulation | Builder | Low to medium | In contract
E07 | Internal finishes | Plasterboard, doors, skirting, painting, floor coverings | Builder, floor coverings often PC | Low to medium | In contract
E08 | Kitchen, bathrooms and laundry | Cabinetry, benchtops, tiles, tapware, shower screens, waterproofing | Builder, often with PC items | Medium to high. Selections drive it | In contract
E09 | Services | Electrical, plumbing, hot water, air conditioning, solar | Builder or specialist trades | Medium. Upgrades add up | In contract
E10 | External works | Driveway, paths, fencing, letterbox, clothesline, landscaping, turf | Often you, outside the contract | High. Easy to forget or underestimate | Outside contract
E11 | Connections | Electricity, water, sewer, NBN, meters | Builder or you (check) | Medium. Long runs cost more | In contract
E12 | Owner-supplied items | Anything you buy for the builder to install | You | Medium. Delivery, quantity and compliance | Owner-supplied
E13 | Fit-out after handover | Window coverings, flyscreens, appliances not included | You | Medium | Outside contract
E14
E15
E16
Allowances: prime cost (PC) items and provisional sums (PS). The allowance is the builder's price; your estimate is what you actually want (3.3, 3.7)
Elements
PC items and PSs
Forecast costs (before contingency)
Contract price (builder's prices for rows in the contract, including PC and PS allowances)
Contingency, as a % of the contract price (3.5: at least 10%; see the guide below) | [10 empty] | 10%
Contingency
STARTING BUDGET (forecast costs + contingency)
Contingency guide (3.5)
| Your situation |  | Contingency to consider
| Fixed-price project home, flat block, few allowances, selections finalised before signing |  | About 10% of the contract price
| Sloping or rocky block, or large provisional sums for site works |  | 10–15%
| Many PC items and PSs, or selections not yet made |  | 15% or more
| Custom design before tender, or a cost-plus contract |  | 15–20%
| Owner-builder |  | Plan on the higher end
Keep contingency separate from upgrades. Release it only for the unforeseen or unavoidable, and in stages: keep most of it until the enclosed (lock-up) stage, and a final slice until after handover.

## Register
Cost-control register
Chapter 3.6. What will this home cost me in the end? Update it every time you agree to anything with a price, and before every progress payment.
Forecast final cost |  | Total budget |  | Contingency at contract |  | Contingency used |  | Contingency remaining |  | Contingency used, % |  |  | Unallocated Log rows
# | Register line | Group | Budget at contract | Contract amount | Approved variations | PC/PS adjustments | Owner-supplied and extras committed | Spent or committed to date | Pending (quoted, not agreed) | Still to come (your estimate) | Forecast final cost | Over / (under) budget | Notes
Totals
Summary in the book's format (3.6): forecast final cost = contract price + approved variations + PC/PS adjustments + owner-supplied items + extras outside the contract
Line |  |  | Budget at contract | Spent or committed to date | Forecast final
1. Contract price
2. Approved variations |  |  | 0
3. PC/PS adjustments |  |  | 0
4. Owner-supplied items
5. Extras outside the contract
Forecast cost (lines 1–5)
6. Contingency
Total budget

## Log
Log: every priced change, one row each
Chapters 3.6–3.7. Reference (V01, PS-01, PC-01…), date, register line, type, description, amount, status and evidence. GST-inclusive.
Status: Quoted = pending (in the forecast only). Agreed, Signed, Invoiced, Paid = committed. Rejected = ignored. Credits are negative amounts.
Reference | Date | Register line | Type | Description | Amount (+/−) | Status | Evidence | Notes | Counts as

## Allowances
Allowances: tracking PC items and PSs until they're closed
Chapter 3.7. Items come from the Cost plan. The builder's margin applies only to overruns; under-runs are credits. Your contract sets the margin.
Ref | Item | Type | Allowance | Selection quantity | Selection rate | Your selection or actual cost | Builder's margin on overrun | Adjustment | Closed? (Y/N) | In the Log (committed) | Check
Total adjustments
• Close PC items at selection: work out the adjustment and put it in the Log straight away. Don't wait for the builder's claim.
• Check the quantity. A tile allowance per square metre only works if the area is right; check it includes 8–10% for waste.
• Ask for the evidence on every PS: invoices, quotes, dockets and photos.
• Look for credits. If a PS comes in under the allowance, you should get a credit. The margin applies only to overruns.

## Progress claims
Progress claims: reconcile every claim before you pay
Stage | What should be finished | Contract % | Scheduled cumulative % | Scheduled amount | Stage reached? (Y/N) | Stage amount claimed | Variations and adjustments on this claim | Total claimed | Date claimed | Checked? (Y/N) | Amount paid | Date paid | Cumulative paid | % of current price paid | Cumulative stage claims % | Check
Deposit | Contract signed | 5%
Base | Slab poured (or floor frame done) | 15%
Frame | Wall and roof frames up, inspected | 20%
Enclosed (lock-up) | Roof, external walls, windows and external doors in | 25%
Fixing | Internal linings, cabinets, doors, architraves, skirtings | 20%
Practical completion | Finished and ready to hand over | 15%
Totals
One-line reconciliation (3.9)
Original contract price (from the Cost plan) |  |  |  |  | Contract price + approved variations ± PC/PS adjustments − total claimed to date (including this claim) = amount still to be claimed. Do this sum at every claim. The amount still to be claimed should be enough to finish the job. On the example schedule, once the frame stage is paid you've paid 40% and 60% remains. If more has been claimed than the schedule allows for the stage actually reached, payments are running ahead of the work: raise it in writing before you pay, and follow your contract's dispute process.
+ Approved variations (from the Register)
± PC/PS adjustments (from the Register)
= Current contract price
− Total claimed to date (including this claim) |  |  |  |  | Before you pay a claim, check (3.9)
= AMOUNT STILL TO BE CLAIMED |  |  |  |  | 1. The stage is the right one, and the work for it is actually finished.
Your estimate of the cost to finish (value of the contract work still to do, plus unclaimed adjustments) |  |  |  |  | 2. The claim equals the contract percentage of the current contract price.
Stage reached (last stage marked Y) |  |  |  |  | 3. Each variation on the claim matches a signed variation, at the agreed amount, and is due.
Scheduled cumulative % for the stage reached |  |  |  |  | 4. PC and PS adjustments have evidence. Credits for under-runs appear.
Stage claims to date, % of contract price |  |  |  |  | 5. Nothing is claimed twice: check against the Log and previous claims.
Stage payments to date, % of contract price |  |  |  |  | 6. The running total doesn't run ahead of the value of the work done.
Variations and adjustments claimed to date
Approved variations and PC/PS adjustments (Register)
Amount still to be claimed − your cost to finish

## Cash flow
Cash flow: when the money has to be there
Chapter 3.8. Your money goes first. Variations, adjustments, owner-supplied items and extras are usually paid in cash.
Construction loan for the contract |  |  | Your cash share of the contract price (contract price − loan)
Your cash available (savings, deposit funds) |  |  | Peak cash needed from you
Buffer to keep (valuation delays, late claims) |  |  | Lowest cash left
Expected month | Event | Contract claim | Other payments due | Other payments amount | Interest and rent | Paid from | Loan drawdown | Cash needed from you | Running cash needed | Cash left | Running loan drawn | Notes
Contract signed: deposit
Base stage
Frame stage
Enclosed (lock-up)
Fixing stage
Practical completion
After handover
Totals
• Contract claims start from the Progress claims schedule. Type over them with your own amounts, and put each event in the month you expect it.
• Lenders usually want your funds spent before theirs: the sheet uses your cash share of the contract price first, then the loan.
• Unless your lender approves an increase, assume variations, overruns and owner-supplied items come from your cash. Tell your lender early about anything large.
• Add interest on each drawdown and your rent. Update the forecast at every stage.