## Project planner
New product project planner
Template courtesy of Harvey Lee
[15 empty] | Plan Duration | [5 empty] | Actual Duration | [5 empty] | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| Phase | Objective | Activity | R | A | C | I | Plan start | Plan duration | Actual start | Actual duration | % complete | Periods
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Plan and Test | Pre-Launch | Diagnose market | Research TAM, competition, secondary & primary research | PMM | PMM | MI | M | 1 | 2 | 1 | 2 | 100%
|  | Segment, position, targeting | Define the holy trinity of SPT to know who we're targeting | PMM | PMM | MI | M | 2 | 2 | 1 | 3 | 100%
|  | Introduce basic level of knowledge & understanding | Domain training cross team | PO | PPM | PT MI | M | 1 | 2 | 1 | 2 | 50%
|  | Agree and alignment to KPIs, goals, deliverables, timelines | Project Kick Off Meeting | PPM | GT PMM PO | PO GT | M | 3 | 1 | 3 | 1 | 50%
|  | Form partner marketing plan | Meet Charity partners | PT | PMM | GT | M | 3 | 2 | 3 | 2 | 50%
|  | Internal Marketing plan | Develop launch promotion plan | GT PMM | GT PMM | PO | M | 3 | 4 | 3 | 1 | 25%
|  | GTM Toolbox Readiness | Align and ensure all elements in state of readiness | PMM | PMM | PO GT | M | 4 | 2 | 4 | 2 | 50%
|  | Test technical readiness (beta) | Dogfood feature in app cross group | PO | PO | PMM | M | 5 | 2 | 5 | 1 | 0%
|  | Go-No-Go Decision | Readiness meeting cross group | PMM | PO | M | M | 6 | 1 | 6 | 1 | 0%
Promote and measure | Launch | Launch public marketing and promotion | In app, Web, Partner, PR, SEO, Key Words | GT | GT | PMM PO | M | 7 | 4 | 7 | 4 | 0%
|  | Check performance (daily) | KPIs & Objective check. Immediate corrective action if required | PO PMM | PO PMM | GT | - | 7 | 4 | 7 | 4 | 0%
|  | Check performance (weekly) | KPIs & Objective check. Immediate corrective action if required. Report | PO PMM | PO PMM | GT | M | 7 | 4 | 7 | 4 | 0%
|  | Learn, reiterate on-the-go | Get user and market feedback | PMM | PMM | PO MI | M | 11 | 1 | 11 | 1 | 0%
Evaluate and Reiterate | Post-Launch | Evaluate/Review KPI performance in v.1 | Version review meeting. Agree next iteration | PO PMM | PO PMM | GT MI | M | 12 | 2 | 12 | 2 | 0%
|  | Broaden Charity partner network | Onboard 2nd wave of partners. Use v.1 data insights | PT | PT | PO PMM | M | 14 | 2 | 14 | 2 | 0%
|  | Introduce new features | Result of KPI evaluation, latest insights and data | PO | PO | PMM MI | M | 15 | 2 | 15 | 2 | 0%
|  | Test technical readiness (beta) | Dogfood feature in app cross group | PO | PO | PMM | M | 16 | 2 | 16 | 2 | 0%
|  | v.2 of Project Plan for v.2 would be worked on in parallel to v.1 but with timing offset (non-linear) | [5 empty] | 0 | 0 | 0 | 0 | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0%

## GTM toolbox
GTM toolbox
Audience
Tool | Purpose | Source | Responsible | Management | Central | Markets
Business Case | Why Donations? White paper on the donations market, user insights, partner landscape. Includes the Opportunity for [company] and what [company] gains. Set interim Objectives and KPIs | Various | PMM | X | X
Survey Data | Share insights gained from early 'register your interest', partner insights and Revolut user surveys. | Partners and Revolut | PMM | X | X
In App Beta | Internal or External. Get early insights before launch and have time to reiterate where required. | In-App | PO | X | X | X
GTM document | Partner focused guidance on how to GTM in co-operation with specific partners. Define what [company] can do for them, what they can do for [company]. | Partners, Internal Partner Department | PT/PMM |  | X | X
Messaging Guide | Key document for definitive positioning, key messages, final KPIs, market overview, rules of engagement (do's/don'ts), legals, etc. | PMM | PMM |  | X | X
Budget allocation | Ensure if budget required for marketing collateral or promotion, it’s clear and well thought out to reach the KPIs and allocated to appropriate stakeholders | GT | GT |  | X | X
Partner Marketing Toolkit | Partner-specific brand guidelines, Visual IDs, etc. | Partners | PT |  | X | X
Promotional Planning Document | PR, Seo, Key Words, Partner Marketing, In-app, own channels. | GT | GT |  | X | X

## Working group
Working group
Function | Acronym | Role | Responsibilities
Product Owner | PO | Lead on product team | Deliver product to market fit
Product Marketing Manager | PMM | Voice of customer in nexus role | Ensure market fit by using data and insights. Lead GTM planning cross group
Growth Team | GT | Execute growth and marketing plan | Deliver marketing plan to achieve agreed KPIs
Market Insights Manager | MI | Assist group with insights externally and internally to specific domain | Help cross group to build a more insightful product and sell smarter
Partner Marketing Manager | PT | Secure and onboard Charity partners | Deliver right partners for right markets to scale. Ensure best fit and joint marketability
Management (appropriate level) | M | Key decision makers | Go-no-go, POC for escalations and approvals