## Slide 1
Systems & Processes | Learn what currently exists across stakeholder groups for reporting, analysis and Rhythm of the Business (business calendar) | Scope consolidation, optimization and define goals and objectives across key stakeholder groups | Propose 1st version of new business calendar, KPI benchmarks, analytics dashboard as single source of truth
Domain & Product | Immerse self in Product and Domain learning across all key business’s/products | Scope business & product priorities, focus, and key gaps | Draft proposal on product focus aligned to business objectives, mitigation plan to address gaps and insight plans to discover new opportunity
Personal & Team Development | Define role and responsibility, agree KPI and 90-day S.M.A.R.T. plan | Team hiring needs, scope job descriptions, start hiring process | Complete 1st stage interview process. Define 1-year Objectives for self and to-be-hired team
Business Growth & Priorities | Listen to and document stakeholder priorities, Corporate goals | Asses the ‘how’ we get to goals/objectives with what is known at 30-60 days | Proposal of short/medium/long term growth and where Product Marketing adds value to drive product success
90 Day Plan
Understand
Assess
Optimize
Days
Days
Days
30
60
90

## Slide 2
90 Day Plan – S.M.A.R.T. Plan (System & Processes)
Specific | Build understanding of the internal business calendar (Rhythm of the Business aka. RoB) | Build understanding of the internal analytical/reporting systems at present | Assess business needs for reporting | Define goals and objectives/KPIs across key stakeholder groups for reporting purposes | Propose aligned ‘single source of truth’ for reporting | Proposal for complete Rhythm of the Business calendar to match new growth/marketing team agenda
Measurable | Deliver one document with known RoB | Deliver one document with known reporting tools | Deliver one SWOT/Pro-Con-Conclusion doc for all tools in line with business needs assessment | Deliver one document with set of aligned objectives/KPIs across key stakeholder groups | Deliver one dashboard/scorecard proposal around which data sources can be inputs to pre-agreed KPI’s | Deliver one defined business calendar of key meetings cross group
Achievable | Core information obtainable and already available from other stakeholders | Core information obtainable and already available from other stakeholders | Assessment is done based on what exists today | In interest of key stakeholder alignment | Scoping is achievable, tangibility to a dashboard would be TBC | With already good proximity of the team, value of such meetings will be understood (after pre-briefing given)
Relevant | Key to understand internal business cadence for planning, reporting, reviewing | Sources of measurement, are required to measure what we do | Assessment required to be able to make future proposal to meet business needs | Required to ensure what we are measuring and what success looks like cross group | An easy-to-use tool for measurement is always relevant | Important for key stakeholder groups to meeting formally to discuss the business performance and opportunity
Time-Bound | Within 30 days of start date | Within 30 days of start date | Within 30-60 days of start date | Within 60-90 days of start date | By 90 days of start date | By 90 days of start date
Learn what currently exists across groups in reporting, analysis and Rhythm of the Business (business calendar)
Scope consolidation, optimization and define goals and objectives across key stakeholder groups
Propose 1st version of new business calendar, KPI benchmarks, analytics dashboard as single source of truth

## Slide 3
90 Day Plan – S.M.A.R.T. Plan (Domain & Product)
Specific | Training on <Product Name> | Learn customer journey’s | Take a walk in the client's shoes | SWOT on key products | Positioning documents for <Product Name> | Research proposal to build out on what’s known and the known gaps
Measurable | Demonstratable ability to demo product in 30-60 days | Demonstrable ability to articulate basic CJ for each product | Meet/shadow six clients of Connect | Three SWOTS, one for each product line | One/two-page document with positioning framework and RTB | One plan based on customer-focus
Achievable | By spending time with product team for hands on training, based in London | CJ maps that currently exist (assumed) shared/walked through with me | Get sales/account managers to set up meetings at client's premises | With 60 days immersive learning and collaboration behind me | Output is a simple PPT slide(s) | Prioritize budget towards goal, in case of constraint, use form of direct-to-client methods
Relevant | <Product Name> is the key product in the portfolio, deep knowledge required | Closeness to the ‘how’ customers take their journey with <Product Name> paramount to own understanding/thinking | Being ‘in-field’ gives the context that quantitative insights can’t give | View of SWOT across stakeholder’s, key to alignment of challenges and opportunities cross group | Key to understand where product sits in market and customers mind. Does the product reality match or exceed the product promise? | You can never know enough about your clients. Deep insights are a lifeblood of PM
Time-Bound | Within 30 days of start date | Within 30-60 days of start date | Within 60-90 days of start date | By 60-90 days of start date | Within 90 days of start date | Within 90 days of draft plan approval
Immerse self in Product & Domain learning
Scope business priorities & key gaps
Draft proposal to product focus

## Slide 4
90 Day Plan – S.M.A.R.T. Plan (Personal & Team Development)
Specific | Agree 90-day plan for self | Scope KPI’s for future aligned measurement on what success looks like (PMM team) | Write Job Descriptions for each PPM role | Draft 1-year MBO (Management by Objectives) | Define team learning plan | PM Team charter
Measurable | One bought-into document from line manager based around S.M.A.R.T. Objectives | One page of definitions of measurement across various touch points | Deliver three JD’s | One set of annual MBO’s | Create one opportunity per quarter for team to learn as whole or individuals | One single page document
Achievable | Simple and aligned document owned and delivered by self | Yes, with up to 60 days immersive learning and collaboration behind me | Once some basic assessment done by self | Yes, once some intermediate assessment done by self | Pool previous learnings and insights to new learning plan | Alignment to objectives of the PMM Team will form part of the basis of team charter
Relevant | Aligned Management by Objective (MBO) agreement | Marketing that’s measurable is key | JD’s essential to hiring process | This is a basic business requirement | Creating a learn-it-all culture/share-it-all culture will help contribute to growing a high performing team | PMM team and stakeholders know what team is responsible for, what team is aligned to and the way the team works (values, etc.)
Time-Bound | Within 30 days of start date | Within 30-60 days of start date | Within 30-60 days of start date | Within 60-90 days of start date | Within 60-90 days of start date | Within 60-90 days of start date
Define role and responsibility, agree KPI and 90-day S.M.A.R.T. plan
Team hiring needs, scope job descriptions, start hiring process
Complete 1st stage interview process. Define 1-year Objectives for self and to-be-hired team

## Slide 5
90 Day Plan – S.M.A.R.T. Plan (Business Growth & Priorities)
Specific | Shadow stakeholders to learn more about their roles, value and challenges | Communicate the value of Product Marketing as a new function and what it means to other stakeholder groups | Market sizing and total addressable market sizing exercise | Map historical business performance to addressable market size and highlight share trends (<Product Name> + competition) | Portfolio relationship matrix | Product Funnel Optimization
Measurable | Shadow one stakeholder per group/team | One presentation to each key stakeholder group to highlight value of PMM to them | By excel file with all relevant data contained (3rd party source) | By excel file with all relevant data contained (3rd party source) plus internal revenue/user data | One PPT presentation with product offering by segment/size. Feature cross-fertilization where possible (allowing for correct level of insights available) | Document tracking the product funnel performance
Achievable | One day per stakeholder per group | Approach to cross-group stakeholders in call to realize new value creation and ways to work together | Assumed that 3rd party able to or already does supply such data | Assumed that 3rd party able to or already does supply such data (as previous Objective) | In basic form at least | With assistance of Product Team and data team
Relevant | Leaning more about other groups key to PPM function in a nexus role | As PMM is a new function in the team, it’s very relevant to introduce it properly | Totally relevant to understand the ‘size of the prize’ | Measuring and tracking our ‘slice’ of the ‘prize’ is key to this specific ongoing KPI | Understanding the relationships in portfolio critical to selling right product to right audience at right time | Understanding adoption, conversion, churn and usage rates one of the keys to product success
Time-Bound | Within 30 days of start date | Within 30 days of start date | Within 30-60 days of start date | Within 60-90 days of start date | Within 60-90 days of start date | Within 90 days of start date
Listen to and document stakeholder priorities, Corporate goals
Asses the ‘how’ we get to goals/objectives with what is known at 30-60 days
Proposal of short/medium/long term growth and where Product Marketing adds value to drive product success forward